## Sheet1
Schedule |  | : | Upgrade Laser Marking For XV8000LK | [7 empty] | Seen |  | Verified |  | Approved
Section |  | : | SD | [5 empty] | Name :
Prepared By |  | : | Zulhisham Tan | [5 empty] | Signature :
Date |  | : | 20th Oct '2012 | [5 empty] | Date :
Remark |  | : | To deploy PX/FC software which is server based application.
No. | Items/To Do List |  |  | 22nd Oct '2012 | [9 empty] | Remark
|  |  |  | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 |  | 16:00 | 17:00
1. | Upgrade to Windows XP Service Pack 3.
2. | Setup Marking Layout for XV8000LK.
3. | Deploy PX/FC software - ActiveProc.
4. | Trial Run & Bug Fix.
5. | Join data to Taping 100% Marking Inspection.
6. | PE/Prod System Verification.
Software distribute over the network
Software utilizes Server resources
Up to 85% System efficiency Improve !!!